## Daily burndown chart
Story | Assignee | Hours remaining (Nov 11) | Hours remaining (Nov 13) | Hours remaining (Nov 15) | Hours remaining (Nov 18) | Hours remaining (Nov 20) | Hours remaining (Nov 22)
As an admin, I want to publish and unpublish an auction | Garrett | 1 | 1
As an admin, I want to enter a live item winner | Tristan | 4 | 0
As a bidder, I want to list the items I am bidding on | Zion | 4 | 0
As an admin, I want to show all winners | Zion | 4 | 4
As a bidder, I want to scan a QR code to view an item | Garrett | 4 | 4
As a bidder, I want to view won items with a total price | Zion | 1 | 0
Implement time-based silent auction starting/shutdown (optional) |  | 6 | 6
Little Tweaks |  | 2 | 2
Total |  | 26 | 17
Day | Hours remaining
1 | 26
2 | 17
3
4
5
6
Day | Hours ideally remaining
1 | 26
2 | 20.8
3 | 15.6
4 | 10.4
5 | 5.2
6 | 0